## WBS
Setting Details | Function/Screen | Feature | UC | Function/Screen Details | Plan | Replan | SRS | SRS-Due | SDS | SDS-Due | IT-TC | IT-TC-Due | Status | FE | FE-Due | BE | BE-Due | Notes
1 | Home Page | Common | View Home Page | Show the static contents and include the web header & footer as in the Mockups sheet Allow the guest to submit the contact information in a chosen category | Iter1 | Iter5 | Viet |  |  |  | Viet |  | Tested | Hoang | 2022-10-03 | Quan
2 | Dashboard | Common | View Dashboard | Show the sample dashboard information where the data are taken from below APIs (ref https://morioh.com/p/57a8d79967b5 for more details) the page include common Admin Header, Admin Footer, and Nav Bar as in the mockup screen - Covid India Data API: https://www.covid19india.org/ - Saved calls for covid19india (Import this json in postman): https://www.getpostman.com/collections/2afb23eddb8accf94c3e | Iter1 | Iter5 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan
3 | User Login | Common | Login System | Authenticate user information - Fields: Email, Password, Capcha; - Page Links: Reset Password, Register Allow Google Login using the FPT @fpt.edu.vn account. In case the user has not existed yet, then a new user would be registered into the system and the random-generated password would be sent to the registered email (along with other appropriate notification messages) Fix handle error khi login bằng tài khoản inactive | Iter1 | Iter1 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan
4 | Forgot Password | Common | Manage User Information | Allow the user to reset his/her password in case he/she forgot it - Expiable new password link would be sent to the email for resetting - Flow: Email -> Reset Link (Expirable) -> New Password, Verifying Password Cái này ok ko cần fix gì | Iter1 | Iter1 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan
5 | Register | Common | Manage User Information | Allow the user to register his/her access to the system: - Just input limited fields (full name, email, capcha), (password) - Đã thêm 2 field password và password confirm, cho phép user tự chọn password luôn k cần generate rồi sent qua mail - Random access password would be sent to the user via registered email (along with other appropriate notification messages) - The user can by-pass registering with Google log-in | Iter1 | Iter1 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan
6 | User Profile | Common | Manage User Information | Allow the user to view & edit his/her own profile information - User can change the avatar, full name, user name, mobile and view others (email, role) - In case the user is trainee, he/she can input/change his/her address, company, position (cần update thêm những properties này) - Page Links: Password Change | Iter1 | Iter1 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan | 2022-10-04
7 | Password Change | Common | Manage User Information | Allow the user to change his/her password (current password need to be provided along with new passwords) Cái này ok ko cần fix gì | Iter1 | Iter1 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan
8 | System Setting | Admin | Manage Setting | List out the current Settings information. From this page, the user can link to the Setting Details page for adding new or updating a specific Setting. - Filters: Type, Status - Search: by Title or Value - Columns: Id, Type, Title, Value, Display Order, Status - Row Actions: View/Edit, Activate/Deactivate - Status: Active, Inactive Cái này ok ko cần fix gì | Iter1 | Iter1 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan |  | Sort by column
9 | System Setting Details | Admin | Manage Setting | Allow the user to input the Setting information for adding or updating - Fields: Type, Title, Value, Display Order, Status, Description - The user can not change the setting type when updating the Setting (không đc sửa type khi update) -> done | Iter1 | Iter1 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan
10 | System Setting Add | Admin | Manage Setting | Allow the user to input the Setting information for adding or updating - Fields: Type, Title, Value, Display Order, Status, Description - The user can not change the setting type when updating the Setting (không đc sửa type khi update) -> done | Iter1 | Iter1 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan
11 | System Permissions | Admin | Configure System Permissions | Configure the page-access permissions for each of the system roles | Iter1 | Iter5 | [6 empty] | Pending | Hoang |  | Quan | 2022-10-05
12 | Web Supports | Supporter | Manage Web Contact | List out the web contacts that are not assigned to any Supporter user or supporter-assigned ones (the Supporter leader can see all the Web contacts). From this page, the user can link to the Web Contact Details page for adding new or updating a specific Web Contact. Phân thành supporter member và supporter leader -Supporter member chỉ thấy những contact của mình, và những contact chưa có supporter -Supporter leader thấy tất cả các contact | Iter2 | Iter3 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan
13 | Web Support Details | Supporter | Manage Web Contact | Allow the user to change the Response & Status + view other Web Contact information - The Supporter leader can change/assign the Supporter information - On submitting the page, if there is not any Supporter assigned, then the current logged-in user would be added as the Supporter for the relevant Web Contact -Supporter leader: Chỉ định (assign) những contact nào cho những supporter nào -Supporter member: Edit status. response của web contact detail (không edit được username supporter được chỉ định, nếu webcontact detail đó chưa có supporter đc chỉ định, mặc định supporter đấy sau khi save xong sẽ đc update (option này đã ok) | Iter2 | Iter3 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan
14 | User Authorization | System | N/A | Show/hide system menu (main, sider) following the role permissions Check the case when user enter URL directly in the Address box of the browser: - In case the user has not logged-in yet or the log-in session has expired, User Login page would be shown to authenticate user before coming back to the entered URL - If the logged in user has no right the the relevant page, the error page would be shown Sidebar hiển thị chính xác những page nào mà role đó được vào, nếu token expired -> đẩy ngược về trang login bắt login lại Nếu cố tình vào trang không có đủ quyền -> redirect sang /access-denied | Iter2 | Iter5 | [6 empty] | Pending | Hoang |  | Quan
15 | User Management | Admin | Manage User Account | List out the current Users information. From this page, the user can link to the User Details page for adding new or updating a specific User. Cái này ok ko cần fix gì | Iter2 | Iter3 | Phong |  |  |  | Viet |  | Tested | Hoang |  | Chinh
16 | User Details | Admin | Manage User Account | Allow the user to input the User information for adding or updating - The password is encrypted & the admin can not see or change it - On adding new user, the random password would be sent to the registered email UserAdd screen: Hiện tại đang có 2 field pass và confirm pass cho phép admin tự set password cho user -> bỏ 2 field này, password sẽ được generate rồi gửi qua mail | Iter2 | Iter3 | Phong |  |  |  | Viet |  | Tested | Hoang |  | Chinh |  | Update roles, cần check lại status
17 | User Add | Admin | Manage User Account | Allow the user to input the User information for adding or updating - The password is encrypted & the admin can not see or change it - On adding new user, the random password would be sent to the registered email UserAdd screen: Hiện tại đang có 2 field pass và confirm pass cho phép admin tự set password cho user -> bỏ 2 field này, password sẽ được generate rồi gửi qua mail | Iter2 | Iter3 | Phong |  |  |  | Viet |  | Tested | Hoang |  | Chinh |  | Update roles, cần check lại status
18 | Subject Management | Manager | Manage Subject | List out the current Subjects information (the Manager user can see only the Subjects that he/she is being assigned). From this page, the user can link to the Subject Details page for adding new or updating a specific Subject. Manager chỉ có thể nhìn thấy những subject mà mình được assign Admin : Thấy hết, có dropdown filter manager Manager: Chỉ thấy những subject mà mình assign -> ẩn filter manager k cần thiết | Iter2 | Iter3 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan
19 | Subject Details | Manager | Manage Subject | Allow the user to input the Subject information for adding or updating (the Manager user can change the expert & description information - in the HTML format) Fix description subject từ text thường sang html Q: HTML -> Markdown (https://www.markdownguide.org/getting-started/) ckeditor | Iter2 | Iter3 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan | 2022-10-03
20 | Subject Add | Manager | Manage Subject | Allow the user to input the Subject information for adding or updating (the Manager user can change the expert & description information - in the HTML format) Fix description subject từ text thường sang html Q: HTML -> Markdown (https://www.markdownguide.org/getting-started/) ckeditor | Iter2 | Iter3 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan | 2022-10-03
21 | Class Management | Manager | Manage Class | List out the Classes in the system - The user can link to the Class Details, Attendance Tracking & Class Evaluations pages - The Trainer & Supporter users have also accesses to this page + The Trainer and Supporter users can see the Classes they are assigned + The links to the Attendance Tracking & Class Evaluations pages + The Supporter can change the Class status directly on this page or link to the Clas Details page for changing some class information (trainer, status, description)c | Iter2 | Iter3 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Chinh
22 | Class Details | Manager | Manage Class | Show the list of the Class data fields for viewing, updating or newly adding - The Manager user can update the Class information (except for the Subject) - The Supporter & Trainer user can view the Class information; The Supporter user can change some class information (trainer, status, description) | Iter2 | Iter3 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Chinh |  | thay packageId bằng subjectID trong bảng class
23 | Class Add | Manager | Manage Class | Show the list of the Class data fields for viewing, updating or newly adding - The Manager user can update the Class information (except for the Subject) - The Supporter & Trainer user can view the Class information; The Supporter user can change some class information (trainer, status, description) | Iter2 | Iter3 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Chinh |  | thay packageId bằng subjectID trong bảng class
24 | Class Trainees | Trainer | Manage Trainee | List out the Trainees for a specific class in the system - The list also include the evaluated grades of the trainees (calculated automatically) - When changing trainee status to Dropped Out, the user need to input the dropout date - The Trainer also have the same access rights as the Supporter to the trainees list of the classes that he/she are assigned - From this page, the user can link to the Trainee Import & Trainee Details pages Status của trainee: dropout = null, inactive = 0, active = 1 | Iter2 | Iter3 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Chinh |  | status (bit): null (dropout), 0 (inactive), 1 (active)
25 | Trainee Import | Trainer | Manage Trainee | This is a pop-up screen where the user can import the new trainee list into a specific class - The import file should include limitted trainee information (full name, email) - New class trainees would be added into the selected class. In case any user has not existed yet, then a new user would be registered into the system and the random-generated password would be sent to the registered email (along with other appropriate notification messages) Status mặc định của trainee khi import vào là inactive | Iter2 | Iter3 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Chinh
26 | Trainee Details | Trainer |  | Allow the user to input class trainee information for updating - The Trainer can also update class trainee information - Trainee basic information are read-only: full name, user name, email - Class trainee evaluation are read-only: on-going evaluation, final evaluation, topic evaluation - Class trainee information are editable: status, drop-out date, note Hiện tại: tất cả manager supporter trainer đều có thể sửa status, dropout date, note Hỏi: ai có thể sửa? | Iter2 | Iter3 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Chinh
27 | Subject Setting | Manager |  | List out the Settings for a specific active subject in the system. From this page, the user can link to the Subject Setting Details page for adding new or updating a specific Setting. | iter3 | Iter3 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan |  | status (bit): 0 (inactive), 1 (active)
28 | Subject Setting Details | Manager |  | Allow the user to input Subject Setting information for adding or updating. The user can not change the Subject and setting type when updating the Setting | iter3 | Iter3 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan
29 | Subject Setting Add | Manager |  | Allow the user to input Subject Setting information for adding or updating. The user can not change the Subject and setting type when updating the Setting | iter3 | Iter3 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan
30 | Class Settings | Trainer + Manager |  | List out the Settings for a specific active class in the system. - The Supporter can view the list of Settings for the classes that he/she are assigned (read-only) - From this page, the user can link to the Class Setting Details page for adding new or updating a specific Setting. Supporter: không add, không edit status (activate, reactivate) | iter3 | Iter3 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan |  | status (bit): 0 (inactive), 1 (active)
31 | Class Setting Details | Trainer + Manager |  | Allow the user to input Class Setting information for adding or updating - The user can not change the Class and setting type when updating the Setting - The Supporter can view the Class Setting information only (không đc edit) | iter3 | Iter3 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan
32 | Class Setting Add | Trainer + Manager |  | Allow the user to input Class Setting information for adding or updating - The user can not change the Class and setting type when updating the Setting - The Supporter can view the Class Setting information only (không đc edit) | iter3 | Iter3 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan
33 | Subject Assignments | Manager |  | List out the Assigments for a specific active subject in the system. From this page, the user can link to the Assignment Details page for adding new or updating a specific Assignment. | iter3 | Iter3 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Chinh |  | status (bit): 0 (inactive), 1 (active)
34 | Assignment Details | Manager |  | Allow the user to input Assignment information for adding or updating (the user can not change the subject on updating the Assignment) | iter3 | Iter3 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Chinh
35 | Assignment Add | Manager |  | Allow the user to input Assignment information for adding or updating (the user can not change the subject on updating the Assignment) | iter3 | Iter3 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Chinh
36 | Evaluation Criteria | Manager |  | List out the Evaluation Criteria for a specific subject assignment in the system. From this page, the user can link to the Eval Criteria Details page for adding new (by cloning an existing Evaluation Criteria or adding brand new one) or updating a specific Evaluation Criteria Status: Inactive (0), Active (1) | iter3 | iter4 | Viet |  |  |  | Phong |  | Tested | Hoang |  | Chinh |  | status (bit): 0 (inactive), 1 (active)
37 | Evaluation Criteria Details | Manager |  | Allow the user to input Evaluation Criteria information for adding or updating (the user can not change the subject & assignment on updating the Evaluation Criteria) | iter3 | iter4 | Viet |  |  |  | Phong |  | Tested | Hoang |  | Chinh
38 | Evaluation Criteria Add | Manager |  | Allow the user to input Evaluation Criteria information for adding or updating (the user can not change the subject & assignment on updating the Evaluation Criteria) | iter3 | iter4 | Viet |  |  |  | Phong |  | Tested | Hoang |  | Chinh
39 | Class Assignments | Trainer |  | List out the Milestones for a specific active class in the system. - The Supporter can view the list of Milestones for the classes that he/she are assigned (read-only) - From this page, + The user can link to the Milestone Details page for viewing or updating a specific Milestone. + The Trainer can link to the New Milestone page for adding new Milestone - Status: Open -> In Progress -> Closed + The user can delete the Open milestone physically + When the user change the milestone status from Open to In-Progress, a pop-up would be shown informing the user about the teaming status & get confirmation about the teaming way to work on the milestone assignment (team-work, individually) + give him/her another option to come to the Team List page to configure milestone teaming + When the user change the milestone status from In-Progress to Closed, a pop-up would be shown informing him/her about the milestone evaluation status/results, explaining him that he/she can not update the evaluation for the closed milestone & get his/her confirmation on that + give him/her another option to come to the Milestone Evaluations page to view & update/adjust evaluations | iter3 | iter4 | Phong |  |  |  | Viet |  | Tested | Hoang |  | Quan
40 | New Class Assignments | Trainer |  | Allow user to input Milestone information for adding new: assignment, title, description, from date, to date There is not any case where one assignment is "linked" to more than one milestones or vise versa After submitting the page: - The information from selected assignment would be copied to the newly created Milestone: + The assignment title & description are copied to the new milestone's title & description + The activate evaluation criteria are copied to the new milestone's evaluation criteria | iter3 | iter4 | Phong |  |  |  | Viet |  | Tested | Hoang |  | Quan
41 | Class Assignments Details | Trainer |  | The Supporter and Trainer can view Milestone's information. The Trainer can edit Milestone's information (except for changing the linked assignment). | iter3 | iter4 | Phong |  |  |  | Viet |  | Tested | Hoang |  | Quan
42 | Class Evaluation List | Trainer |  | List out the Evaluation Criteria for a specific class milestone in the system. The Supporter can view the Evaluation Criteria for the classes that he/she are assigned From this page, the user can link to the Class Eval-Criteria Details page for adding new (by cloning an existing Class Evaluation Criteria or adding brand new one) or updating a specific Class Evaluation Criteria Status: Inactive (0), Active (1) | iter3 | iter4 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Chinh |  | status (bit): 0 (inactive), 1 (active)
43 | Class Evaluation Details | Trainer |  | Allow the user to input Class Evaluation Criteria information for adding or updating - The user can not change the class & milstone on updating the Class Evaluation Criteria - The Supporter is not allowed to change any information | iter3 | iter4 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Chinh
44 | Class Evaluation Add | Trainer |  | Allow the user to input Class Evaluation Criteria information for adding or updating - The user can not change the class & milstone on updating the Class Evaluation Criteria - The Supporter is not allowed to change any information | iter3 | iter4 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Chinh
45 | Class Schedule | Supporter Only |  | List out class schedules - Columns: Slot, Topic, Date, From Time, To Time, Room, Take Attendance, Action - Actions: + View/Edit: link to the Schedule Details page to view/edit the relevant class schedule + Take Attendance: link to Attendance Details page to add/edit the class attendance of the relevant slot - this link is available only durent the training day of that slot - Global actions: + View Attendance: link to Attendance Tracking page + Add New: link to the Schedule Details page to add new class schedule - The Trainer have similar permissions as the Supporter on this page - Status: Inactive (0), Active (1), Attendance-Taken (null) | iter3 | iter4 | Viet |  |  |  | Phong |  | Tested | Hoang |  | Chinh |  | status (attendance-taken): 0 (inactive), 1 (active)
46 | Class Schedule Details | Supporter Only |  | Allow the Supporter/Trainer to input schedule information for adding new or editing the relevant class schedule. The user is not allowed to change the attendance-taken schedule | iter3 | iter4 | Viet |  |  |  | Phong |  | Tested | Hoang |  | Chinh
47 | Class Schedule Add | Supporter Only |  | Allow the Supporter/Trainer to input schedule information for adding new or editing the relevant class schedule. The user is not allowed to change the attendance-taken schedule | iter3 | iter4 | Viet |  |  |  | Phong |  | Tested | Hoang |  | Chinh
48 | Schedule Attendace Class Attendance | Trainee |  | List out class schedules of the selected class & the student attendance status for each schedule Columns: Slot, Topic, Date, From Time, To Time, Room, Take Attendance, Attendance Status |  | iter5 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Chinh
49 | Trainee Groups | Trainer |  | "See the Mockup - The Supporter & Trainee can view the team list & team details - Member Actions: Change Group, Remove Member, Set As The Leader - The screen just shows the active team-working assignments in the Assignment filter - Global Actions: + Create Groups or Reset Groups - link to New Groups page to create/re-create new team set + Remove Groups - remove or un-attached current team set from the selected milestone + Add New Group - add new group to change (move) a specific member to - Group Actions: + Add New Trainee: add trainee(s) from waiting list into the selected team + Group Details: link to GroupDetails to view and/or edit the team + Activate/Deactivate: activate or deactiavate the team - The above actions are not allowed for the team sets which are ""attached"" to the in-progress or closed milestones Status: Inactive (0), Active (1)" | iter3 | iter4 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan
50 | New Groups | Trainer |  | Allow the user to create groups or regroups See the Mockup - note to add one more tab called Clone Group with the similar layout as the Reuse Group; Clone Groups would create new team set "attached" to the milestone (by copying the current team configurations) instead of re-using the current team set in the Reuse Groups | iter3 | iter4 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan
51 | Group Details | Trainer |  | "Allow the user to input team information for updating relevant team or adding new team to the team set of the milestone. - Fields: team code, topic name, status, description - When creating new team, the default status value is Active " | iter3 | iter4 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan
52 | Attendance Tracking Attendance Reports | Trainer |  | Allow the Supporter/Trainer to view the class trainees' attendance status of all the class schedules Status: Present (1), Late (0), Absent (null) | iter4 | iter5 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Chinh
53 | Attendance Detail Attendance Tracking | Trainer |  | Allow the Supporter/Trainer to add/edit the class attendance of the relevant schedule | iter4 | iter5 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Chinh
54 | Issue Management | Trainee |  | Show the list of the group issues, group by requirement(similar layout as the Team List page). Trainers can access the issues list of the classes that he/she is assigned - Columns: Checkbox, Title, Milestone, Type, Assignee, Deadline, Status + Filters: Group(0-1), Assignment(1), Milestones, Types, Assignees, Statuses; Search by ID or Title + Status: Open, CStatus1, CStatus2,.., CStatusN -> Closed (CStatus ~ Customized Status, those are taken from the class_setting) - If issues are not linked to any requirements, they are listed in the General Requirement group - Page Actions + Add new requirement or issue to a specific requirement => nếu issue không có type thì nó là requirement + Choose to change type, status, or assignee(1 issue assign cho 1 student) of a specific issue + Show details: link to the Issue Details page to view the details of a specific issue + Change Work-Issue-Links for the issues (choosing from the milestone requirements) + Batch Change: Type, Status, Assignee, or Work-Issue-Links for the selected issues | iter4 | iter5 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan |  | test bằng 3 acc: trainer, leader, member
55 | Issue Details | Trainee |  | Allow the user to input the issue information for adding or updating: - Basic issue information: title, milestone, type, assignee, deadline, status - Linked issues (similar way as GitLab, but limitted to choose from the requirements) Trainer have similar right as the trainee from all team; Only trainer or team leader can: - Add, edit the requirements - Change the type of other issues to requirements The updating issue can be added for the evaluated requirement only | iter4 | iter5 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan |  | test bằng 3 acc: trainer, leader, member
56 | Issue Add | Trainee |  | Allow the user to input the issue information for adding or updating: - Basic issue information: title, milestone, type, assignee, deadline, status - Linked issues (similar way as GitLab, but limitted to choose from the requirements) Trainer have similar right as the trainee from all team; Only trainer or team leader can: - Add, edit the requirements - Change the type of other issues to requirements The updating issue can be added for the evaluated requirement only | iter4 | iter5 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan |  | test bằng 3 acc: trainer, leader, member
57 | Class Requirements | Trainee |  | Tương tự như issue nhưng data chỉ có title, milestone, assignees. | iter4 | iter5 | Viet |  |  |  | Phong |  | Tested | Hoang |  | Quan |  | test bằng 3 acc: trainer, leader, member
58 | Class Requirement Detail | Trainee |  | Tương tự như issue nhưng data chỉ có title, milestone, assignees, description. Chỉ có trainer và leader được sửa | iter4 | iter5 | Viet |  |  |  | Phong |  | Tested | Hoang |  | Quan |  | test bằng 3 acc: trainer, leader, member
59 | Class Requirement Add | Trainee |  | Tương tự như issue nhưng data chỉ có title, milestone, assignees, description. Chỉ có trainer và leader được sửa | iter4 | iter5 | Viet |  |  |  | Phong |  | Tested | Hoang |  | Quan |  | test bằng 3 acc: trainer, leader, member
60 | Submit List | Evaluation Trainer/Trainee |  | Show the list of the team-assigned submits and the trainee's submits (for the milestones where the class trainees do the assignment individually ~ related to non-team-working assignments or the milestones that there no team set "attached" to). - Filters: Assignments, Milestones, Teams, Trainees, Statuses - Columns: Id, Assignment, Milestone, Team, Trainee, Status, Last Updated At - Submit Status: Pending (null), Submitted (0), Evaluated (1) - Actions: + Link to the New Submit popup screen: the trainee to add/update individual submit + Link to the New Submit popup screen: the team leader to add/update team's submit + Link to the Groups Evaluation: the trainer to view/update team evaluations for the submit - The user can create the new submit for in-progress milestone. He/she can update the submit in case that submit has not been evaluated. | iter4 | iter5 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan/Chinh
61 | Assignment Submit | Evaluation |  | Allow the trainee to create new or update an existing submit for a specific in-progress milestone - Only one zip file (size <= 10 MB) are allow to upload & renamed before saving to the server - Beside the milestone and the submit zip file, the users also choose the requirements which are ready to submit this time from the list of available requirements (requirements those have not been submitted or evaluated yet in other milestones) - The new submit is just for individual assignment and with the in-progress milestone where the trainee has not had a new submit yet | iter4 | iter5 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan/Chinh
62 | Submit Details | Evaluation |  | Show the details of the submit along with the list of requirements which are done or updated in the milestone (or all updated requirements & newly completed requirements for final milestone) - Columns: #, Requirement, Assignee, Status, Complexity, Quality, Grade/10; - Filters* Assignees, Status. - Status: Submitted(null), Recjected(0), Evaluated (1); for final milstone, there is one more which is implied status (Updated) The trainer have access to all the trainees issues, the trainee have access to his/hers only If the milestone is in progress, then the trainer can (the trainee has read-only access) - Reject or Un Reject a specific requirement - Link to the Work Evaluation screen (for each requirement) to evaluate the work - Import work evaluations (for all the requirements; importing file template is taken via exporting curent list; file fields: fields: Id, Requirement, Assignee, Status, Complexity, Quality) In case the relevant milestone is closed, then the trainer/trainee can - Export work evaluations (for all requirements) - Link to the Issue Details screen (for each requirement) | iter4 | iter5 | Phong |  |  |  | Viet |  | Tested | Hoang |  | Chinh
63 | Class Evaluations | Evaluation |  | Tham khảo FUGE (Điểm quá trình) - Import/Clear in dropdown context menu - Show/Hide in checkbox dropdown context menu - Link to Group Evaluations (global action) & Trainee Evaluations (row action) - note: trainer có thể action, trainee chỉ có thể view * các cột: số thứ tự sv, user name, full name, GPA (điểm tổng), OG (điểm quá trình), Final (điểm cuối kì), Comments, Class Assignment 1 -> Class Assignment n (các milestone) * action: - filter tổng bằng class - 1 cái Show Class Assignments dropdown list sẽ xòe xuống các select box của các Class Assignment, select để hiện cột Class Assignment tương ứng (có thể chọn nhiều), ngoài dùng để select, mỗi Class Assignment có thêm 1 ">" button và khi ấn vào sẽ xòe ra list 3 button chức năng : + Clear Mark: xóa hết điểm của Class Assignment tương ứng + Import Mark: là 1 pop-up để import file excel Class Assignment, file sẽ có 4 cột user name, full name, mark và cmt + Recaculate Mark: dành cho trường hợp ko ghi hay import điểm trực tiếp mà chấm theo các tiêu chí, sau đó hệ thống sẽ tự tính toán điểm của từng tiêu chí để ra điểm chuẩn cho Class Assignment -search bằng user name hoặc full name -Edit Mark: dùng để khi trainer muốn nhập tay điểm cho từng sv trong từng Class Assignment, lúc ấn vào nút "Edit Mark" thì nút này sẽ tự ẩn hoặc disible, hiện ra 2 nút là "Save Change" và "Reverse Change" (reset) -export mark | iter4 | iter5 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan/Chinh
64 | Assignment Evaluations | Evaluation |  | Tham khảo Mockup Note: -bonus asssignment evaluation range -2 -> 2 -dòng Group và chức năng Copy Group Evals chỉ hiện cho các milestone có group * các cột: check box, user name, full name, mark, WG, WR, Bonus, Comments, Criteria 1 -> Criteria n (các tiêu chí đánh giá), SDS -WR: số LOC có được sau khi trainer chấm -WG: WG = WR/ExpectedWork * 10 +ExpectedWork lấy từ work evaluation * action: - filter bằng Class Assignments và Group - 1 cái Show Evaluation Criteria dropdown list sẽ xòe xuống các select box của các Criteria, select để hiện cột Criteria tương ứng (có thể chọn nhiều), ngoài dùng để select, mỗi Criteria có thêm 1 ">" button và khi ấn vào sẽ xòe ra list 2 button chức năng : + Clear Evaluations: xóa hết điểm của Criteria tương ứng + Import Evaluations: là 1 pop-up để import file excel Criteria, file sẽ có 4 cột user name, full name, eva và cmt -search bằng user name hoặc full name -Edit Mark: dùng để khi trainer muốn nhập tay điểm cho từng sv trong từng Eva, SDS, bonus, lúc ấn vào nút "Edit Mark" thì nút này sẽ tự ẩn hoặc disible, hiện ra 2 nút là "Save Change" và "Reverse Change" (reset) -Copy Group Evals: copy điểm của dòng group sang điểm của tất cả sv trong group | iter4 | iter5 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan/Chinh
65 | Work Evaluation | Evaluation |  | Allow trainer to evaluate the submitted or updated work, trainee can view detailed evaluation for him/her here. The screen layouts are as in the Mockup -note: trainer có thể action, trainee chỉ có thể view *gồm 2 tag gồm Work Evaluation và New Work Evaluation *Work Evaluation -các trường text cứng: full name, user name, group name (nếu có), milestone name -action: evaluate, reject -các trường: function, function description, complexity, quality, work result, evaluation comment/reject reason +complexity (dropdown list button): độ khó gồm simple (60), medium(120), complex(240) +quality (dropdown list button): mức độ hoàn thành gồm low(50%), medium(75%), high(100%) +work result (disible): work result = complexity * quality *New Work Evaluation (link từ row final của submit details) -các trường text cứng: full name, user name, group name (nếu có) -action: submit, view details update (link sang trang work update) -các trường: scope, last complexity, last quality, last work result, last evaluation comment, update, update complexity, update quality, update work result +scope, last complexity, last quality, last work result, last evaluation comment: là những trường lấy dữ liệu từ kết quả đánh giá gần nhất +update: là nội dung update mới nhất của evaluation +update complexity, update quality, update work result: những đánh giá mới | iter4 | iter5 | Viet |  |  |  | Phong |  | Tested | Hoang |  | Quan
66 | Trainee Evaluation | Evaluation |  | See the Mockup Link to Group Evaluations -note: trainer có thể action, trainee chỉ có thể view -dành cho trainee *gồm 2 tag gồm Evaluation và Work Evaluation *Evaluation -các trường text cứng: full name, user name, assignment -action: back -các trường: total assignment evaluation, criteria name n, work evaluation, bonus/penality + total assignment evaluation: điểm tổng + criteria name n: các tiêu chí đánh giá và điểm cho mỗi tiêu chí + work evaluation: điểm quá trình *Work Evaluation -các cột: id, requirement, complexity, quality, comment, action +action: update (dẫn tới work evaluation) | iter4 | iter5 | Viet |  |  |  | Phong |  | Tested | Hoang |  | Quan/Chinh
67 | Work Updates | Trainee |  | Giảng viên : Link từ WorkEval sang màn WorkUpdate Với những requirement đã submit và được chấm điểm ----> Work Eval ( read only) Từ màn Work Eval giảng viên muốn đánh giá lại hoặc xem lần đánh giá ( comment ) trước, sau lần comment đã cập nhật gì Nội dung xem chi tiết trong WorkUpdate thông qua trường Update ( Ở trường Upate chỉ hiện thông tin tổng thể ) trong WorkEval ( New WorkEvalution ) Học viên : Link từ TraineeEval sang màn WorkUpdate Các nhóm sinh viên sẽ thêm, sau mỗi lần sửa đã cập nhật được những gì, sửa được những gì Gồm các thông tin : Thuộc Requirement nào, Milestone nào, Cmt gì ( Ví dụ sau lần nhận xét 1 của thầy có 5 lỗi, học viên sẽ thêm 5 lỗi đó, sửa được lỗi nào sẽ cập nhật code lên và note lại ) Gồm các cột : ID, Update Name, Milestone, Ngày giờ cập nhật, Action ( Edit và Xoá ) Với Edit sẽ có 1 popup ( Update Information ) Có thể Thêm mới Update Đối với học viên : Màn này gọi từ Trainee Eval sang ( đánh giá cho từng Requiremnet ) ----> chuyển sang Update | iter5 | iter5 | Phong |  |  |  | Phong |  | Tested | Hoang |  | Quan
68 | Post Detail | Trainer |  |  | iter5 | iter5 | Phong |  |  |  | Viet |  | Tested | Hoang |  | Quan
69 | My Schedule | Trainer |  | Hiển thị các schedule của GV trong ngày, từ đó có link để chuyển sang add/edit attendance của lớp học | iter5 | iter5 | Phong |  |  |  | Viet |  | Tested | Hoang |  | Chinh
70 | Post View | Trainee |  |  | iter5 | iter5 | Phong |  |  |  | Viet |  | Tested | Hoang |  | Quan
71 | Post List | Trainee |  |  | iter5 | iter5 | Viet |  |  |  | Viet |  | Tested | Hoang |  | Quan

## API
API_URL |  |  | https://lms-app-1.herokuapp.com/ |  |  | token issue management | glpat-daPcKVEzdLJnGmiNEQoA
GOOGLE LOGIN TEST URL |  |  | https://deepakaggarwal7.github.io/react-social-login/?fbclid=IwAR3bM_t8eD4B38XehrAh0u2Lue5GjjTWdn5tJJ5R_kS2KYiOnTeX4tB1fhY
LINK TEST |  |  | https://docs.google.com/spreadsheets/d/1ixbdx6dbtnvRCZjQBQ7NL3P-AK9NIVmEfBQf3DFK0Wo/edit?usp=sharing | [6 empty] | Email default | xucxichbo@doivl.com
Admin = A Manager = M Supporter = S Trainer = Tr Trainee = Te
Screen | Role | Method | API | Input | Processing | Output | Due date | Status
Screen | Role | Method | API | Input | Processing | Output | Due date | Status |  | Password default | 123456
Login |  | POST | /auth/login | email, password | Check existed email | token | 18/9/2022 | Completed
| All | GET | /user |  | verify token | fullName, username, email, mobile, avatar_url, roles ,perission | 18/9/2022 | Completed | Hiển thị username , fullName , email , roles,avatar
|  | POST | /auth/login-google | idToken,clientID |  | token
Register |  | POST | /auth/register | fullName, email,link | Create unverifed user , sent verify mail to user |  | 18/9/2022 | Completed
Resend Verify |  | PUT | /auth/resend-verify | email,link
Verify User |  | GET | /auth/verify?token=... |  | set user status to ACTIVE
Change Password | All | PUT | /user/update-pass | oldPassword , newPassword | update password |  | 20/9/2022 | Completed
ForgetPassword |  | PUT | /user/forgot-pass | email,link | sent mail to user with link to reset password |  | 20/9/2023 | Completed
|  | PUT | /user/forgot-processing?token=... | newPassword | set user password to newPassword |  |  | Completed
Profile Update | All | PUT | /user/update-profile | avatarBase64, fullName, mobile , username | update user profile |  | 24/9/2022 | Completed | Update username
Setting List | A | GET | /api/setting | params: page. limit, q, filterType, filterStatus |  | list, total page | 24/9/2023 | Completed | Ko hiện role, api ,screen , type
Setting Detail | A | GET | /api/setting-detail/{id} | params: id |  | Setting info | 24/9/2023 | Completed
Setting Get Filter | A | GET | /api/setting-filter |  |  | list type , list status |  | Completed | Ko hiện role, api ,screen , type
Setting Edit | A | PUT | /api/setting-detail/{id} | description,displayOrder, title | Update setting |  |  | Completed
Setting Activate/Deactivate | A | PUT | /api/setting-status/{id} | params: id | set Setting status to Active/Inactive |  |  | Completed
Setting Add | A | POST | /api/setting-add | settingTitle , settingValue , status , description , displayOrder, typeValue | add new setting |  |  | Completed
Get Permission | A | GET | /api/permission |  |  | list of router in FE |  | Completed
Edit Permission | A | PUT | /api/permission | List of [ roleValue,url,get,edit,delete,add ] | Update permission |  |  | Completed
Web Contact Get Subject |  | GET | /api/contact-subjects |  |  | array all subject |  | Completed
Web Contact |  | POST | /api/contact-add | categoryValue, fullName, email, mobile, message |  |  |  | Completed
Web Contact List | S | GET | /api/contact | params: page. limit, q, filterCategory, filterStatus, filterStatus |  | return web contact list |  | Completed
Web Contact Detail | S | GET | /api/contac-detail/{id} |  |  | return web contact detail |  | Completed
Iter2
UserList | A | GET | /api/user | params: page. limit, q, filterRole, filterStatus |  | list, total page | 29/9/2022 | Completed
UserDetail | A | GET | /api/user-detail/{id} | params: id | update user |  | 29/9/2022 | Completed
User Activate/Deactivate | A | PUT | /api/user-status/{id} |  |  |  |  | Completed
User Edit | A | PUT | /api/user-detail/{id} | role, note |  |  |  | Completed
User Get Filter | A | GET | /api/user-filter |  |  | list roles, list status |  | Completed
Subject List | A, M | GET | /api/subjects | params: page. limit, q, filter(Manager, Expert, Status) |  | list subjects |  | Completed | hiển thị username của manager, expert
Subject Details | A, M | GET | /api/subjects-detail/{id} |  |  | subjects info |  | Completed
Subject Activate/Deactivate | A, M | PUT | /api/subjects-status/{id} |  |  | set status to ACTIVATE/INACTIVE |  | Completed
Subject Edit | A, M | PUT | /api/subjects-detail/{id} | subjectCode , subjectName , subjectStatus , body , managerUsername , expertUsername |  |  |  | Completed | Edit theo username của manager và expert
Filter | A, M | GET | /api/subjects-filter |  |  | Manager email, Expert email, Status |  | Completed | filter theo status và username của manager,expert
Subject Add |  | POST | /api/subjects-add | subjectCode, subjectName, subjectStatus , body , managerUsername , expertUsername | add new Subject |  |  | Completed
Class List | M, Tr | GET | /api/class | 8 params: page. limit, q, filterTrainer, filterSupporter, filterTerm, filterBranch, filterStatus |  | list, total page | 2022-01-10 | Completed
Class Details | M, Tr | GET | /api/class-detail/{id} | param : id | update class |  | 2022-01-10 | Completed
Class Activate/Deactivate | M, Tr | PUT | /api/class-status/{id} | param: id |  |  |  | Completed
Class Edit | M, Tr | PUT | /api/class-detail/{id} | param: id ¦¦ status, code, subjectCode , term, bracnch, description, trainer, supporter |  |  |  | Completed
Filter | M, Tr | GET | /api/class-filter |  |  | list trainer, list status |  | Completed
ClassAdd | M, Tr | POST | /api/class-add | status, code, subjectCode , term, bracnch, description, trainer, supporter |  |  |  | Completed
Completed
Trainee List |  | GET | /api/trainee | 5 params : page, limit, q, filterClass, filterStatus |  |  |  | Completed
Trainee import |  | POST | /api/trainee-import/${code}
Trainee export
Trainee update status |  | PUT | /api/trainee-status/{userId}/{classCode} | 2 params: userId, classCode |  |  |  | Completed
Trainee set dropout |  | PUT | /api/trainee-dropout/{userId}/{classCode} | 2 params: userId, classCode |  |  |  | Completed
Trainee detail |  | GET | /api/trainee-detail/{userId}/{classCode} | 2 params: userId, classCode
Setting Subject List
Iter3
Subject Setting list | M | GET | /api/subject-setting | q , limit , page , filterType , filterSubject , filterStatus |  | list subject setting |  | Completed
Subject Setting detail | M | GET | /api/subject-setting-detail/{id} |  |  | detail of subject setting |  | Completed
Subject Setting add | M | POST | /api/subject-setting-add | subjectCode , typeValue , settingTitle , settingValue , status , description, displayOrder |  |  |  | Completed
Subject Setting edit | M | PUT | /api/subject-setting-detail/{id} | settingTitle , settingValue , status , description, displayOrder |  |  |  | Completed
Subject Setting filter | M | GET | /api/subject-setting-filter |  |  |  |  | Completed
Subject Setting activate/deactivate | M | PUT | /api/subject-setting-status/{id}
Completed
Class Setting list | T,S | GET | /api/class-setting | q , limit , page , filterType , filterClass , filterStatus |  |  |  | Completed
Class Setting detail | T,S | GET | /api/class-setting-detail/{id} |  |  |  |  | Completed
Class Setting add | T | POST | /api/class-setting-add | classCode , typeValue , settingTitle , settingValue , status , description, displayOrder |  |  |  | Completed
Class Setting edit | T | PUT | /api/class-setting-detail/{id} | settingTitle , settingValue , status , description, displayOrder |  |  |  | Completed
Class Setting filter | T,S | GET | /api/class-setting-filter
Class Setting activate/deactivate | T | PUT | /api/class-setting-status/{id}
Assignment List | M | GET | /api/assignment |  |  |  |  | Completed
Assignment Detail | M | GET | /api/assignment-detail/{id} | params: id |  |  |  | Completed
Assignem update status | M | PUT | /api/assignment-status/{id} | params: id |  |  |  | Completed
Assignment add | M | POST | /api/assignment-add |  |  |  |  | Completed
Assignment update | M | PUt | /api/assignment-detail/{id} | params: id |  |  |  | Completed
Assignment-filter | M | GET | /api/assignment-filter |  |  |  |  | Completed
Eval Criteria List | M | GET | /api/criteria?classCode=.. | params: classCode(required) |  |  |  | Completed
Eval Criteria Detail | M | GET | /api/criteria-detail/{id} | params: id |  |  |  | Completed
Eval Criteria update status | M | PUT | /api/criteria-status/{id} | params: id |  |  |  | Completed
Eval Criteria add | M | POST | /api/criteria-add |  |  |  |  | Completed
Eval Criteria update | M | PUt | /api/criteria-detail/{id} | params: id |  |  |  | Completed
Eval Criteria-filter | M | GET | /api/criteria-filter?classCode=... | params: classCode(required) |  |  |  | Completed
Milestone list | Tr | GET | /api/milestone | param: q, limit, page, filterClass, filterStatus , filterAssignment |  |  |  | Completed
Milestone edit | Tr | PUT | /api/milestone-detail/1 | fromDate, toDate ,title, description |  |  |  | Completed
Milestone add | Tr | POST | /api/milestone-add | assignmentId , classesCode , status , description , title ,toDate , fromDate |  |  |  | Completed
Milestone detail | Tr | GET | /api/milestone-detail/1 |  |  |  |  | Completed
Milestone to inprogress | Tr | PUT | /api/milestone-inprogess/{id} |  | Set milestone to inprogress |  |  | Completed
Milestone to closed | Tr | PUT | /api/milestone-closed/{id} |  | Set milestone to closed |  |  | Completed
Group list | Tr,S,Te | GET | /api/group | param : q,limit,page,filterMilstone , filterStatus |  |  |  | Completed
Group edit | Tr | PUT | /api/group-detail/{id}/{milestoneId} | { "groupCode":"SWPG23", "topicName":"Iteration 1", "description":"Reach 700 LOC", "status":"0" } |  |  |  | Completed
Group detail | Tr,S,Te | GET | /api/group-detail/{id} |  |  |  |  | Completed
Group filter | Tr,S,Te | GET | /api/group-filter/{classCode} |  |  |  |  | Completed
Group activate/deactivate member | Tr | PUT | /api/group-status/{userName}/{groupId}
Group remove member(from group to waiting list) | Tr | DELETE | /api/group-member-remove/{username}/{groupId}/{milestoneId} |  | Remove member from group |  |  | Completed
Group add member (from wait list to group) | Tr | POST | api/group-member-add/{userName}/{groupId}/{milestoneId} |  |  |  |  | Completed
Group set Leader | Tr | PUT | /api/group-set-leader/{userName}/{groupId} |  | Set leader to member with userName |  |  | Completed
Group change status | Tr | PUT | /api/group-status/{groupId} |  |  |  |  | Completed
Group change (from old group to new group) | Tr | PUT | /api/group-change/xucxixh/9/8 (userName , groupId, newGroupId) |  |  |  |  | Completed
Group add(create a new group and attach to current milestone) | Tr | POST | /api/group-add/{username}/{milestoneId} | { "groupCode":"group 4", "topicName":"TEST2", "description":"this is group 5" } |  |  |  | Completed
Group detach(detach group from current milestone) | Tr,S,Te | PUT | /api/group-detach/{groupId}/{milestoneId} |  |  |  |  | Completed
Group activate/deactivate | Tr,S,Te | PUT | /api/group-status/{groupId} |  |  |  |  | Completed
Create/Reset group set (create a new group set for current milestone, replace current group set if exist) | Tr | PUT | /api/group-set/{milestoneId} |  |  |  |  | Completed
Group set filter | Tr | GET | /api/group-set-filter/{milestoneId} |  |  |  |  | Completed
Removes Group (detach all group from current milestone) | Tr | DELETE | /api/group-removes/{milestoneId} |  | Remove group all group from current Milestone |  |  | Completed
Reuse Group filter | Tr | GET | /api/group-reuse-filter/{milestoneId}
Resuse Group | Tr | PUT | /api/group-reuse/{milestoneId}/{reuseMilestoneId} |  | Apply group config of milestone to current milestone |  |  | Completed
Clone Group | Tr | POST | /api/group-clone/{milestoneId}/{cloneMilestoneId} |  | Clone group of milestone and assign to current milestone |  |  | Completed
Completed
Class eval criteria list | Tr, S | GET | /api/class-criteria | param: q, limit, page, filterMilestone, filterStatus , filterClass |  |  |  | Completed
Class eval criteria detail | Tr, S | GET | /api/class-criteria-detail/{id} | param: id |  |  |  | Completed
Class eval criteria add | Tr, S | POST | /api/class-criteria-add |  |  |  |  | Completed
Class eval criteria update status | Tr, S | PUT | /api/class-criteria-status/{id} | param: id |  |  |  | Completed
Class eval criteria update | Tr, S | PUT | /api/class-criteria-detail/{id} | param: id |  |  |  | Completed
Class eval criteria filter | Tr, S | GET | /api/class-criteria-filter |  |  |  |  | Completed
Schedule List | Tr, S | GET | /api/schedule | param: q, limit, page, filterDateFrom, filterDateTo, filterStatus , filterClass
Schedule Detail | Tr, S | GET | /api/schedule-detail/{id} | param: id
Schedule update | Tr, S | PUT | /api/schedule-detail/{id} | param: id
Schedule update status | Tr, S | PUT | /api/schedule-status
Schedule add | Tr, S | POST | /api/schedule-add
Schedule filter | Tr, S | GET | /api/schedule-filter
Issue List | Tr,Te | GET | /api/issue/{classCode} | param: limit ,q , page ,groupId , milestoneId , asignee , statusId ,requirementId ,typeId |  |  |  | Completed
Issue List filter | Tr,Te | GET | /api/issue-list-filter/{classCode} | ?milestoneId= |  |  |  | Completed
Issue detail | Tr,Te | GET | /api/issue-detail/{issueId} |  |  |  |  | Completed
Issue add filter | Tr,Te | GET | /api/issue-add-filter/{classCode} |  |  |  |  | Completed
Issue add | Tr,Te | POST | /api/issue-add/{classCode} | title, description , milestoneId ,statusId , typeId ,description,milestoneId ,asigneeName ,deadline |  |  |  | Completed
Issue edit | Tr,Te | PUT | /api/issue-detail/{issueId} | title, description , milestoneId ,statusId , typeId ,description,milestoneId ,asigneeName ,deadline |  |  |  | Completed
Issue batch update | Tr,Te | PUT | /api/issue-batch-update | issueToUpdate(list of issue id) , updateToApply(statusId , typeId ,asigneeName) |  |  |  | Completed
Requirement add filter | Tr,Te | GET | /api/requirement-add-filter/{classCode} |  |  |  |  | Completed
Issue multichange | Tr,Te | PUT | /api/issue-multichange | issues |  |  |  | Completed
Attendance Tracking | Tr, S | GET | /api/attendance-tracking?filterClass=.. | param: filterClass
Attendance Detail | Tr, S | GET | /api/attendance-detail/{id} | param: id (schedule id)
Attendance Update | Tr, S | PUT | /api/attendance-detail/{id} | param: id (schedule id)
Schedule Attendance | Te | GET | /api/attendance-schedule?filterClass=.. | param: filterClass
Submit list | Tr,Te | GET | /api/submit/{classCode} | param: limit ,q , page ,isGroup,groupId , milestoneId , asignee , statusValue |  |  |  | Completed
Submit list filter | Tr,Te | GET | /api/submit-list-filter/{classCode} | param: isGroup |  |  |  | Completed
New submit filter | Tr,Te | GET | api/new-submit/{submitId} |  |  |  |  | Completed
New submit | Tr,Te | POST | api/new-submit/{submitId} | requirementIds, submitFile
Submit Detail | Tr,Te | GET | /api/submit-detail/{id} | param: id(submit id), q, assigneeFilter, statusFilter
My Class Schedule | Tr | GET | /api/my-schedule
Post list | All | GET | /api/post | Param :limit ,q , page , categoryId , isNotice(true = post trong dashboard) , topView(hiển thị top n post có view cao nhất) |  |  |  | Completed
Post view | All | GET | /api/post-view/{postId} |  |  |  |  | Completed
Post filter | All(login) | GET | /api/post-upload-filter |  |  |  |  | Completed
Post upload | All(login) | POST | /api/post-upload | body :postTitle , categoryId , content , excerpt , content thumbnailBase64 |  |  |  | Completed
Post edit | All(login) | PUT | /api/post-view/{postId} | body :postTitle , categoryId , content , excerpt , content thumbnailBase64 |  |  |  | Completed
Work eval form | Tr | GET | api/work-eval/{submitId}/{workId} |  |  |  |  | Completed
Work eval submit | Tr | POST | api/work-eval/{submitId}/{workId}/{milestoneId} | complexityId , qualityId ,workPoint ,comment
Work eval reject | Tr | PUT | api/work-eval/{submitId}/{workId} | comment
Trainee eval | Te,Tr | GET | api/trainee-result/{submitId} |  |  |  |  | Completed
Work update form | Te,Tr | GET | /api/work-update/{submitId}/{workId} |  |  |  |  | Completed
Work update | Te,Tr | POST | /api/work-update/{submitId}/{workId} | title , description , updateDate , milestoneId |  |  |  | Completed
Work update edit | Te,Tr | PUT | /api/work-update/{updateId} | title , description , updateDate , milestoneId |  |  |  | Completed
Work update delete | Te,Tr | DELETE | /api/work-update/{updateId}
MilestoneEval Form | Te,Tr | GET | api/milestone-eval/{milestoneId} | Param : page , limit,q , groupId , milestoneId |  |  |  | Completed
MilestoneEval Filter | Te,Tr | GET | api/milestone-eval-filter/{classCode} |  |  |  |  | Completed
Milestone Evaluation | Te,Tr | POST | api/milestone-eval/{milestoneId} | evalList |  |  |  | Completed
Class Evaluation |  | GET | api/class-evaluate?classCode=.. | params: q, classCode(required)
Class Evaluation Update Eval |  | PUT | api/class-evaluate-update?classCode= | params: classCode(required)
Class Evaluation Generate |  | PUT | api/class-evaluate-generate?classCode= | params: classCode(required)
Trainee add |  | POST | api/trainee-add?classCode=.. | params: classCode(required)

## Mockup
My Schedule
Show các cột: Class, Module, Topic, From-Time, To-Time, Take Attendance, Action
Action: Take/Edit Attendance -> Link to the Attendance Tracking page
Click link View Attendance Reports -> Link to the Attendance Reports page
Class Evaluations
Assignment Evaluations
Work Evaluations
Submit List
New Submit
Trainee Evaluation

## ERD
Milestone List => New Milestone: chọn Ass -> copy tilte/desc -> edit: title, from-date, to-date, desc -> submit: create milestone record + duplicate ass eval criteria for the milestones
Edit Milestone: edit title, from-date, to-date, desc + show selected assignement (read-only)
Lastest ERD

## Defect
Defect ID | Defect Date | Screen | Status | Title | Description |  | Reported By | Solved By | Solved Date | Solve Description | Recheck By | Recheck Date
[5 empty] | Current | Expect
1 | 2022-10-10 | User Profile | Solved | Notification | After update information, screen show "You have change your password successfully" | After update information, screen show "You have change your profile successfully" | Viet | Hoang | 2022-10-10 |  | Viet | 2022-10-10
2 | 2022-10-10 | User Profile | Solved | Notification | After update image, screen show "You have change your password successfully" | After update image, screen show "You have change your avatar successfully" | Viet | Hoang | 2022-10-10 |  | Viet | 2022-10-10
3 | 2022-10-10 | User Profile | Solved | Edit Avatar | Update Avatar fail | Update Avatar successfully | Viet | Hoang | 2022-10-10 |  | Viet | 2022-10-10
4 | 2022-10-10 | User Profile | Solved | Edit | Reset button did not work with Phone Number field if the default value is null | Reset button is work with Phone Number field if the default value is null | Viet | Hoang | 2022-10-10 |  | Viet | 2022-10-10
5 | 2022-10-10 | User Profile | Solved | Edit | Cancel button did not clean Phone Number field if the default value is null | Cancel button is clean Phone Number field if the default value is null | Viet | Hoang | 2022-10-10 |  | Viet | 2022-10-10
6 | 2022-11-10 | Home Page | Solved | Paginate | Paginate did not working | Paginate return exact result | Viet | Hoang | 2022-11-10 | Pagination correctly | Viet | 2022-12-10
7 | 14/10/2022 | System Settings | Solved | Filter | Can not filter by type | Filter type return exact result | Hoang | Hoang | 15/10/2022 |  | Viet | 16/10/2022
8 | 14/10/2022 | Subject Management | Solved | Filter | Filter by expect do not show all of expect | Filter by expect show all of expect | Viet | Quan | 15/10/2022 |  | Viet | 16/10/2022
9 | 14/10/2022 | Class List | Solved | Filter | Filter by supporter do not show all of supporter | Filter by supporter show all of supporter | Viet | Chinh | 15/10/2022 |  | Viet | 16/10/2022
10 | 14/10/2022 | Web Contact List | Solved | Paginate | Can't access another page | Access another page | Viet | Hoang | 15/10/2022 |  | Viet | 16/10/2022
11 | 14/10/2022 | Web Contact List | Solved | Filter | Can't filter by Category | Filter category return exact result | Viet | Quan | 15/10/2022 |  | Viet | 16/10/2022
12 | 14/10/2022 | Web Contact Detail | Solved | Edit | After edit with empty value of response. Screen show "Something went wrong" | Screen show "Response can't empty" | Viet | Hoang | 15/10/2022 | Missing token | Viet | 16/10/2022
13 | 14/10/2022 | User List | Solved | Paginate | Can't access another page after user used search or filter function except page 1 | Access another page after user used search or filter function | Viet | Hoang | 15/10/2022 |  | Viet | 16/10/2022
14 | 17/10/2022 | User List | Solved | Refresh | Refresh function did not clean search value, so Paginate show error result | Refresh function clean search value | Viet | Hoang | 18/10/2022 | Clear search filter when click Refresh | Viet | 19/10/2022
15 | 17/10/2022 | User List | Solved | Filter | All of filter is not woking parallel with search value | All of filter is woking parallel with search value | Viet | Hoang | 18/10/2022 | Fix search query | Viet | 19/10/2022
16 | 17/10/2022 | User Add | Solved | Email | Create new user successfully with invalid form of email | Create new user fail with invalid form of email | Viet | Hoang | 17/10/2022 | Missing validate email | Viet | 19/10/2022
17 | 17/10/2022 | Seting Add | Solved | Title | Add new with Title field as successful spaces | Can't add new with Title field as successful spaces | Phong | Hoang | 17/10/2022 |  | Phong | 19/10/2023
18 | 17/10/2022 | Seting Add | Solved | Value | Add new with Value field as successful spaces | Can't add new with Value field as successful spaces | Phong | Hoang | 17/10/2022 |  | Phong | 19/10/2024
19 | 17/10/2022 | Seting Detail | Solved | Title | Edit with Title field as successful spaces | Can't edit with Title field as successful spaces | Phong | Hoang | 17/10/2022 |  | Phong | 19/10/2025
20 | 17/10/2022 | Seting Detail | Solved | Value | Edit with Value field as successful spaces | Can't edit with Value field as successful spaces | Phong | Hoang | 17/10/2022 |  | Phong | 19/10/2026
21 | 17/10/2022 | Subject Add | Solved | Code | Add new with Code field as successful spaces | Can't add new with Code field as successful spaces | Phong | Hoang | 17/10/2022 |  | Phong | 19/10/2027
22 | 17/10/2022 | Subject Add | Solved | Name | Add new with Name field as successful spaces | Can't add new with Name field as successful spaces | Phong | Hoang | 17/10/2022 |  | Phong | 19/10/2028
23 | 17/10/2022 | Subject Detail | Solved | Code | Edit with Code field as successful spaces | Can't edit with Code field as successful spaces | Phong | Hoang | 17/10/2022 |  | Phong | 19/10/2029
24 | 17/10/2022 | Subject Detail | Solved | Name | Edit with Name field as successful spaces | Can't edit with Name field as successful spaces | Phong | Hoang | 17/10/2022 |  | Phong | 19/10/2030
25 | 17/10/2022 | Class Trainees | Solved | Filter | Filter is not woking parallel with search value | Filter is woking parallel with search value | Viet | Hoang | 17/10/2022 |  | Viet | 19/10/2022
26 | 17/10/2022 | Trainee Details | Solved | Dropout | Dropout is not woking in the first action | Dropout is woking well at everytime | Viet | Hoang | 17/10/2022 | Fix state | Viet | 19/10/2022
27 | 17/10/2022 | Trainee Import | Solved | Notification | After import fail, screen show "Import Trainee Successfully" | After import fail, screen show "Import Trainee Fail" | Viet | Hoang | 17/10/2022 | Follow requirement | Viet | 19/10/2022
28 | 17/10/2022 | Class Setting Detail | Solved | Edit | Edit fail | Edit Successful | Viet | Hoang | 17/10/2022 |  | Viet | 19/10/2022
29 | 18/10/2022 | Class Settings | Solved | Filter | All of filter is not woking parallel with search value | All of filter is woking parallel with search value | Viet | Hoang | 18/10/2022 |  | Viet | 19/10/2022
30 | 18/10/2022 | Subject Assignments | Solved | Filter | All of filter is not woking parallel with search value | All of filter is woking parallel with search value | Viet | Hoang | 18/10/2022 |  | Viet | 19/10/2022
31 | 19/10/2022 | Assignment Add | Solved | Evaluation Weight | Can input negative number | Input a number between 0 and 100 | Viet | Hoang | 18/10/2022 |  | Viet | 19/10/2022
32 | 19/10/2022 | Subject Assignment | Solved | Refresh | Can't refresh screen to default value | Refresh screen to default value | Viet | Hoang | 18/10/2022 |  | Viet | 19/10/2022
33 | 28/10/2022 | Eval Criteria Add; Eval Criteria Details | Solved | Expected Work | Expected Work can negative | Expected Work's value is between 0 and 100 | Viet | Hoang | 2022-01-11 |  | Viet | 2022-03-11
34 | 28/10/2022 | Eval Criteria Add | Solved | Create | Create Fail | Create Successful | Viet | Chinh | 2022-01-11 |  | Viet | 2022-03-11
35 | 28/10/2022 | Eval Criteria Add | Solved | Create | One field is missing is isWorkEval | No field is missing | Viet | Chinh, Hoang | 2022-01-11 |  | Viet | 2022-03-11
36 | 28/10/2022 | Eval Criteria Details | Solved | Edit | Edit Fail | Edit Successful | Viet | Chinh | 2022-01-11 |  | Viet | 2022-03-11
37 | 28/10/2022 | Eval Criteria Details | Solved | Edit | One field is missing is isWorkEval | No field is missing | Viet | Chinh, Hoang | 2022-01-11 |  | Viet | 2022-03-11
38 | 2022-02-11 | Class Assignments | Solved | Filter | Can not filter by class | Filter class return exact result | Viet | Quan | 2022-05-11 |  | Viet | 2022-06-11
39 | 2022-02-11 | Class Assignments | Solved | Filter | Can not filter by status | Filter status return exact result | Viet | Quan | 2022-05-11 |  | Viet | 2022-06-11
40 | 2022-02-11 | Milestone Details | Solved | Edit | Show Edit button for milestone that has status is In_process or Closed | Hide Edit button for milestone that has status is In_process or Closed | Viet | Hoang | 2022-05-11 |  | Viet | 2022-06-11
41 | 2022-02-11 | Milestone Add | Solved | Title | Can create more than 1 milestone with a title | Can not create more than 1 milestone with a title | Viet | Quan | 2022-05-11 |  | Viet | 2022-06-11
42 | 2022-02-11 | Class Assignments | Solved | Filter | All of filter is not woking parallel with search value | All of filter is woking parallel with search value | Viet | Hoang | 2022-03-11 | Fix filter | Viet | 2022-06-11
43 | 2022-02-11 | Class Assignments | Solved | Paginate | Paginate working wrong, click page 1 then screen show page 2 and opposite | Paginate working well | Viet | Hoang | 2022-03-11 | Fix pagination | Viet | 2022-06-11
44 | 2022-02-11 | MIlestone Add | Solved | Select Assignment | Select them same Subject Assignment for 2 Assignment, screen show "Something went wrong" | Screen show "Subject Assignment were used already" | Viet | Hoang Quan | 2022-03-11 |  | Viet | 2022-06-11
45 | 2022-02-11 | New Group | Solved | Reuse Group | Reuse Group working wrong, Reuse Group is not clean old group before reuse new group | Reuse Group working well | Viet | Hoang, Quan | 2022-03-11 |  | Viet | 13/11/2022
46 | 2022-02-11 | New Group | Solved | Random Group | After user create group by another way then create group by Random Group, it will not working. But Random group is working well if user remove group and create by Random Group | Random Group working well | Viet | Hoang, Quan | 2022-03-11
47 | 2022-03-11 | Issue Management | Solved | Status in Batch Change | 2 Done value | Status have 1 done value | Viet | Chinh | 2022-12-11 |  | Viet | 13/11/2022
48 | 2022-02-11 | Issue Management | Solved | Filter | Filter by Requirement error | Filter requirement return exact result | Viet | Hoang | 2022-12-11 |  | Viet | 13/11/2022
49 | 2022-02-11 | Issue Add | Solved | Requirement | Requirement is not filter by milestone | Requirement is filter by milestone | Viet | Hoang, Chinh | 2022-12-11 |  | Viet | 13/11/2022
50 | 2022-03-11 | Issue Management | Solved | Filter | Filter by Status error | Filter status return exact result | Viet | Chinh | 2022-12-11 |  | Viet | 13/11/2022
51 | 24/11/2022 | Assignment Evaluation | Solved | Notification | After update mark by Copy Group Evaluation function. Screen show "Clear Evaluation successfully!" | After update mark by Copy Group Evaluation function. Screen show "Copy Evaluation successfully!" | Viet | Hoang | 25/11/2022 | Wrong message | Viet | 26/11/2022
52 | 24/11/2022 | Assignment Evaluation | Solved | WP, WG | Screen do not show WG, WP | Screen show WG, WP | Viet | Hoang, Chinh | 25/11/2022 |  | Viet | 26/11/2022
53 | 24/11/2022 | Assignment Evaluation | Solved | WP, WG | No responsive for WG, WP columns | Have responsive for WG, Wp columns | Viet | Hoang | 25/11/2022 | Fixed with of column table | Viet | 26/11/2022
54 | 27/11/2022 | Work Update | Solved | Title | Newly added with the same title successfully | Cannot add new Duplicate Title | Phong | Hoang | 28/11/2022 | Can add new work update with same title | Phong | 27/11/2022
55 | 27/11/2022 | Work Update | Solved | Title | Edit with the same title successfully | Cannot edit Duplicate Title | Phong | Hoang | 28/11/2022 | Can add new work update with same content | Phong | 27/11/2022
56 | 27/11/2022 | Work Update | Solved | Title | Add new with title as successful spaces | Show error message can't add work update with title or content is empty | Phong | Hoang | 28/11/2022 | Need check .trim() and empty | Phong | 28/11/2022
57 | 27/11/2022 | Submit Detail | Solved | Evaluted | Trainer click Evaluate fail | Click Evaluate show pop-up and can evaluate requirement | Phong | Hoang | 28/11/2022 | Missing Quality dropdown | Phong | 27/11/2022
58 | 28/11/2022 | Class Evaluations | Solved |  | Trainer cannot access the Class Evaluation screen | Trainer can access the Class Evaluation screen | Phong | Hoang | 28/11/2022 |  | Phong | 29/11/2022
59 | 28/11/2022 | Sidebar | Solved | My Schedule | No link to access My Schedule | Sidebar has link to access My Schedule | Viet | Hoang | 29/11/2022 | Move 'My Schedule" from sidebar to avatar dropdown in header | Viet | 29/11/2022
60 | 28/11/2022 | User Add | Solved | Role of User | After the add is successful, go back to the screen of the newly added user list without a role, need to Edit to appear | Show Role successfully after Add User | Phong | Hoang Quan | 29/11/2022 |  | Phong | 29/11/2022
61 | 28/11/2022 | System Settings Detail | Solved | Title | Title can be changed to spaces | Title can't be changed to spaces | Phong | Hoang | 29/11/2022 | Fix title with trim() | Phong | 28/11/2022
62 | 28/11/2022 | System Settings Add | Solved | Title | Can add Title is a string of spaces | Can not add Title is a string of spaces | Phong | Hoang | 29/11/2022 | Fix title with trim() | Phong | 28/11/2022
63 | 28/11/2022 | Subject Detail | Solved | Notification | Edit successful but the notification status is red color | Edit successful and the notification status is green color | Phong | Hoang | 29/11/2022 | Fix color | Phong | 28/11/2022
64 | 28/11/2022 | Subject Add | Solved | Notification | Add new successful but the notification status is red | Add new successful and the notification status is green color | Phong | Hoang | 29/11/2022 | Fix color | Phong | 28/11/2022
65 | 28/11/2022 | Class Detail | Solved | Class Name | Class name can be changed to spaces | Class name can not change to spaces | Phong | Hoang | 28/11/2022 | Fix class with trim() | Phong | 28/11/2022
66 | 28/11/2022 | Class Add | Solved | Class Name | Can add Class name is a string of spaces | Can not add Class name is a string of spaces | Phong | Hoang | 28/11/2022 | Fix class with trim() | Phong | 28/11/2022
67 | 28/11/2022 | Subject Settings Detail | Solved | Title | Title can be changed to spaces | Title can not be changed to spaces | Phong | Hoang | 28/11/2022 |  | Phong | 28/11/2022
68 | 28/11/2022 | Subject Settings Add | Solved | Title | Can add Title is a string of spaces | Can not add Title is a string of spaces | Phong | Hoang | 29/11/2022 | Fix class with trim() | Phong | 28/11/2023
69 | 28/11/2022 | Subject Assignments | Solved | Filter by Subject | After switching page filter by Subject does not display data | Filter success | Phong | Hoang | 29/11/2022 |  | Phong | 28/11/2024
70 | 28/11/2022 | Assignment Evaluation | Solved | Edit | Edit Mark Fail (Individual) | Edit Mark Successfully | Viet | Hoang Chinh | 29/11/2022 |  | Viet | 29/11/2022
71 | 28/11/2022 | Assignment Evaluation | Solved | Edit | After edit Mark Fail (Individual), the page is reload to empty page | Edit Mark Successfully | Viet | Hoang Chinh | 29/11/2022 |  | Viet | 29/11/2022
72 | 28/11/2022 | Assignment Evaluation | Solved | Mark | Too many decimals | Taken from the second decimal | Viet | Hoang | 29/11/2022 |  | Viet | 29/11/2022
73 | 28/11/2022 | Class Evaluation | Solved | Import Mark | Can Import a number higher than 10 | Can't Import a number higher than 10 | Viet | Hoang | 29/11/2022 |  | Viet | 29/11/2022
74 | 28/11/2022 | Class Evaluation | Solved | Generate Mark | Generate Mark is not working | Generate Mark is working well | Viet | Hoang Chinh | 29/11/2022 |  | Viet | 29/11/2022
75 | 28/11/2022 | Class Evaluation | Solved | Edit | Cannot be edited mark from row 2 onwards | Edit Mark is working well | Viet | Hoang Chinh | 29/11/2022 |  | Viet | 29/11/2022
76 | 28/11/2022 | Class Evaluation | Solved | Import Mark | Cannot be import mark from row 2 onwards | Import Mark woking well | Viet | Hoang Chinh | 29/11/2022 |  | Viet | 29/11/2022
77 | 28/11/2022 | Class Evaluation | Solved | Edit | Cannot be edited comment for each criteria of each student from row 2 onwards | Edit Comment is working well | Viet | Hoang Chinh | 29/11/2022 |  | Viet | 29/11/2022
78 | 28/11/2022 | Class Evaluation | Solved | Authorization | Trainee can edit | Trainee can view only | Viet | Hoang | 29/11/2022 |  | Viet | 29/11/2022
79 | 28/11/2022 | Class Evaluation | Solved | Generate Mark | Too many decimals | Taken from the second decimal | Viet | Hoang | 29/11/2022 |  | Viet | 29/11/2022
80 | 28/11/2022 | Class Evaluation | Solved | Import Mark | Can import with a file has invalid data | Can not import with a file has invalid data, screen show notification | Viet | Hoang | 29/11/2022 |  | Viet | 29/11/2022
81 | 29/11/2022 | Attendance Report | Solved | Absent Percent | Calculate % absent is incorrect | Calculate % absent is correct | Phong | Hoang Chinh | 29/11/2022 |  | Phong | 2022-01-12
82 | 29/11/2022 | Schedule List | Solved | Attendance Status | Attendance Status after Take Attendance not change from Edit Attendance to Attendance Taken | Attendance Status automatically change from Edit Attendance to Attendance Taken after 3 days | Phong | Hoang | 29/11/2022 |  | Phong | 2022-02-12
83 | 30/11/2022 | New Post | Solved | Create Post | Sometime user can not create post. Error message: "could not execute statement; nested exception is org.hibernate.exception.GenericJDBCException: could not execute statement" | Create post working well | Viet
84 | 30/11/2022 | Subject Details | Solved | Empty value | Can enter empty value | Can not enter empty value | Hoang | Hoang | 2022-06-12 |  | Viet | 2022-06-12
85 | 30/11/2022 | Milestone Add | Solved | Create Milestone | Can't create new milestone. Error message: "could not execute statement; SQL [n/a]; nested exception is org.hibernate.exception.DataException: could not execute statement" | Can not enter empty value | Viet |  |  |  | Viet | 2022-06-12
86 | 2022-02-12 | Submit Details | Solved | Evaluate | Screen be empty. | Screen show evaluate pop-up | Viet | Hoang | 2022-06-12 | Complexity and Quality empty | Viet | 2022-06-12
87 | 2022-02-12 | Assignment Evaluation | Solved | Edit Mark | Screen be empty after edit mark of group (data are still be save) | Screen working good after edit mark of group (data are still be save) | Viet | Hoang | 2022-06-12 |  | Viet | 2022-06-12
88 | 2022-02-12 | Group List | Solved | Move leader | After move a leader out of group, no trainee were set as leader | After move a leader out of group, a trainee will be set as leader | Viet | Hoang | 2022-06-12 |  | Viet | 2022-06-12

## Refer
| URD_LSP | https://docs.google.com/spreadsheets/d/14o-ASodGVV_a66YsWglE0aj6DXKUvO31/edit#gid=190091620
Report1
Report2
Report3 | SRS | https://docs.google.com/document/d/16_aTm5yz_9iCkYFbjJxFdFvLjY2JFyrT/edit?fbclid=IwAR109D13J__JDEsoWyuN52ZUd9AfR2HVmG3IgJ2FUlSWfiej5DnigoJFi5g#heading=h.rqzliyabu461
Report4 | SDS | Report 4 - SDS Document
| Iter Test | https://docs.google.com/spreadsheets/d/1ixbdx6dbtnvRCZjQBQ7NL3P-AK9NIVmEfBQf3DFK0Wo/edit#gid=1841898510
Report 5 | Test Report | https://docs.google.com/document/d/11LPmvohajyA1SQmx73lXwUId3OnJ4UefCk1cELyxuP0/edit?fbclid=IwAR07AD0e6IipjNJI9zjyLcPX96FjsmUGi1q0OaspYnW0J-8kh1TQUcURjU8#
| Unit Test Report | https://docs.google.com/spreadsheets/d/1sjpJAs5WJzYH_SMCBR_ORNTATE2rvs7dPGuVFq99SVg/edit?usp=sharing
Report 6 | User Guide | https://docs.google.com/document/d/1OBRfM9o1rMphtGBjM0d8MfhOItkRgvutqgLai-rfz1M/edit?fbclid=IwAR1jhyGpcD-4YxfDjz_XC-xgA9m3CsQ68nFWGYs1t6_NL9oOai1T-ecAR6E
| System Test | System Test Case.xlsx
| Acceptance Test | https://docs.google.com/spreadsheets/d/1dI8nPTdqCLucFlgaVaWa8w-t2CblaiVz/edit?usp=sharing&ouid=102574364419972569844&rtpof=true&sd=true
Report 7 |  | https://docs.google.com/document/d/1QTerwSYaT2uRka-5ov1v7od2sUVe8e7Br1TfVj2z4RE/edit?usp=sharing | <= LINK MỚI NHẤT
https://docs.google.com/document/d/1iuetPXszx68VJMmp7FzAasA5p-_fz6Cl/edit?usp=sharing&ouid=116313591861591772855&rtpof=true&sd=true
| Guide Docs | https://drive.google.com/file/d/1IEyitF9b6h69F__qsDwvbxBNx2134xEB/view?usp=share_link